## Sheet1
Path z-scores
Activity | Description | Predecessor | Opt. (a) | ML. (m) | Pess. (b) | Expected Time | Variance |  |  | Path | Path Sequence | Path Duration | Path Variance | 112 | 116 | 90 to Activity 11
1 | Codify accounts | None | 16 | 19 | 28 | 20 | 4 |  | Critical Path | 1 | 1->5->7->8->12->14->15 | 114 | 49 | -0.28571 | 0.28571
2 | File articles of unification | None | 30 | 30 | 30 | 30 | 0 |  |  | 2 | 1->6->8->12->14->15 | 76 | 24 | 7.3485 | 8.165
3 | Unify price and credit policy | None | 60 | 72 | 90 | 73 | 25 |  |  | 3 | 2->9->14 | 72 | 5 | 17.8885 | 19.6774
4 | Unify personnel policies | None | 18 | 27 | 30 | 26 | 4 |  |  | 4 | 3->10->15 | 108 | 50 | 0.56569 | 1.1314
5 | Unify data processing | 1 | 17 | 29 | 47 | 30 | 25 |  |  | 5 | 4->11->13->15 | 108 | 108 | 0.3849 | 0.7698 | Path to Activity 11 is 4-11 only
6 | Train accounting staff | 1 | 4 | 7 | 10 | 7 | 1 | [6 empty] | 38.75% | 61.25% | Duration 4 & 11 |  | 86
7 | Pilot run data processing | 5 | 12 | 15 | 18 | 15 | 1 | [8 empty] | Variance 4 & 11 |  | 104
8 | Calculate P & L and balance sheet | 6, 7 | 6 | 12 | 24 | 13 | 9 | [8 empty] | z-score | 0.39223
9 | Transfer real property | 2 | 18 | 27 | 30 | 26 | 4 | [8 empty] | probability | 65.26%
10 | Train sales force | 3 | 20 | 35 | 50 | 35 | 25
11 | Negotiate with unions | 4 | 40 | 55 | 100 | 60 | 100
12 | Determine capital needs | 8 | 11 | 20 | 29 | 20 | 9
13 | Explain personnel policies | 11 | 14 | 23 | 26 | 22 | 4
14 | Secure line of credit | 9, 12 | 13 | 16 | 19 | 16 | 1
15 | End | 10, 13, 14 | 0 | 0 | 0 | 0 | 0
| What is the probability of completing the project by day 112? | [6 empty] | 5 |  | 7
[6 empty] | 1 | [5 empty] | 8 |  | 12
[8 empty] | 6 | [7 empty] | 14
[6 empty] | 2 | [5 empty] | 9
What is the probability of completing the project within 116 days?
[6 empty] | 3 | [5 empty] | 10 | [5 empty] | 15
[6 empty] | 4 | [5 empty] | 11 |  | 13
What is the probability of completing the activity titled “Negotiate with Unions” by day 90? (Activity 11)