## Sheet1
Activity | TP1 | TP2
A | 10 | 10
A (100%) | 30 | X
Reporting End of TP1
PV | 10 |  | bugeted cost of the work scheduled
EV | 20 |  | %complete x orginal budget = 100%x20 = 20 |  |  | budgeted cost of the work performed
AC | 30 |  | actual cost
Variances
Scheduled Variance (SV) |  |  | Earned Value - Planned Value | EV-PV | 10
Cost Variance (CV) |  |  | Earved Valued - Actual Cost | EV-AC | -10
Estimates
BAC |  |  | Budgeted at Completion
EAC |  |  | Estimate at Completion
ETC |  |  | Estimate to Complete
VAC | BAC - EAC |  | Variance at Completion
Indices
CPI | EV/AC | 0.66667 | Cost Performance Index |  | Cost efficiency
SPI | EV/PV | 2 | Schedule Performance Index |  | Schedule efficiency

## Sheet2
[7 empty] | Baseline Budget | [16 empty] | EV | AC | PV
Schedule Information | [6 empty] | Time Period | [15 empty] | 1 | 10 | 10 | 10
ACT/WP | DUR | ES | LF | SL | Total PV |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | [5 empty] | 2 | 20 | 30 | 20
A | 2 | 0 | 2 | 0 | 20 |  | Time Period 1: 10; Time Period 2: 10 | [5 empty] | 3 | 66 | 90 | 60
B | 2 | 2 | 6 | 2 | 15 |  | Time Period 3: 5; Time Period 4: 10 | [5 empty] | 4 | 113 | 150 | 110
C | 4 | 2 | 6 | 0 | 100 |  | Time Period 3: 20; Time Period 4: 30; Time Period 5: 30; Time Period 6: 20 | [5 empty] | 5 | 123 | 200 | 150
D | 3 | 2 | 6 | 1 | 35 |  | Time Period 3: 15; Time Period 4: 10; Time Period 5: 10
E | 3 | 6 | 9 | 0 | 120 |  | Time Period 7: 30; Time Period 8: 40; Time Period 9: 50
F | 2 | 9 | 11 | 0 | 30 |  | Time Period 10: 10; Time Period 11: 20
Total PV by time period | [6 empty] | 10 | 10 | 40 | 50 | 40 | 20 | 30 | 40 | 50 | 10 | 20
Cumulative PV by time period | [6 empty] | 10 | 20 | 60 | 110 | 150 | 170 | 200 | 240 | 290 | 300 | 320
End of TP1
Baseline Budget
Schedule Information | [5 empty] | % Complete | Time Period 1: Time Period
ACT/WP | DUR | ES | LF | SL | Total PV |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | EV | AC | PV | CV | SV
A | 2 | 0 | 2 | 0 | 20 | 50% | Time Period 1: 10 | 10 | 10 | 10
B | 2 | 2 | 6 | 2 | 15
C | 4 | 2 | 6 | 0 | 100
D | 3 | 2 | 6 | 1 | 35
E | 3 | 6 | 9 | 0 | 120
F | 2 | 9 | 11 | 0 | 30
Total PV by time period | [6 empty] | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 0
Cumulative PV by time period | [6 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
End of TP2
Baseline Budget
Schedule Information | [5 empty] | % Complete | Time Period 1: Time Period
ACT/WP | DUR | ES | LF | SL | Total PV |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | EV | AC | PV | CV | SV
A | 2 | 0 | 2 | 0 | 20 | 100% | Time Period 1: 10; Time Period 2: 20 | 20 | 30 | 20
B | 2 | 2 | 6 | 2 | 15
C | 4 | 2 | 6 | 0 | 100
D | 3 | 2 | 6 | 1 | 35
E | 3 | 6 | 9 | 0 | 120
F | 2 | 9 | 11 | 0 | 30
Total PV by time period | [6 empty] | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 20 | -10 | 0
Cumulative PV by time period | [6 empty] | 10 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
End of TP3
Baseline Budget
Schedule Information | [5 empty] | % Complete | Time Period 1: Time Period
ACT/WP | DUR | ES | LF | SL | Total PV |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | EV | AC | PV | CV | SV
A | 2 | 0 | 2 | 0 | 20 | 100% | Time Period 1: 10; Time Period 2: 20 | 20 | 30 | 20
B | 2 | 2 | 6 | 2 | 15 | 33.33% | Time Period 3: 10 | 5 | 10 | 5
C | 4 | 2 | 6 | 0 | 100 | 20% | Time Period 3: 30 | 20 | 30 | 20
D | 3 | 2 | 6 | 1 | 35 | 60% | Time Period 3: 20 | 21 | 20 | 15
E | 3 | 6 | 9 | 0 | 120
F | 2 | 9 | 11 | 0 | 30
Total PV by time period | [6 empty] | 10 | 20 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 90 | 60 | -24 | 6
Cumulative PV by time period | [6 empty] | 10 | 30 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
End of TP4
Baseline Budget
Schedule Information | [5 empty] | % Complete | Time Period 1: Time Period
ACT/WP | DUR | ES | LF | SL | Total PV |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | EV | AC | PV | CV | SV
A | 2 | 0 | 2 | 0 | 20 | 100% | Time Period 1: 10; Time Period 2: 20 | 20 | 30 | 20
B | 2 | 2 | 6 | 2 | 15 | 100% | Time Period 3: 10; Time Period 4: 10 | 15 | 20 | 15
C | 4 | 2 | 6 | 0 | 100 | 50% | Time Period 3: 30; Time Period 4: 40 | 50 | 70 | 50
D | 3 | 2 | 6 | 1 | 35 | 80% | Time Period 3: 20; Time Period 4: 10 | 28 | 30 | 25
E | 3 | 6 | 9 | 0 | 120
F | 2 | 9 | 11 | 0 | 30
Total PV by time period | [6 empty] | 10 | 20 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 150 | 110 | -37 | 3
Cumulative PV by time period | [6 empty] | 10 | 30 | 90 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150
End of TP5
Baseline Budget
Schedule Information | [5 empty] | % Complete | Time Period 1: Time Period
ACT/WP | DUR | ES | LF | SL | Total PV |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | EV | AC | PV | CV | SV
A | 2 | 0 | 2 | 0 | 20 | 100% | Time Period 1: 10; Time Period 2: 20 | 20 | 30 | 20
B | 2 | 2 | 6 | 2 | 15 | 100% | Time Period 3: 10; Time Period 4: 10 | 15 | 20 | 15
C | 4 | 2 | 6 | 0 | 100 | 60% | Time Period 3: 30; Time Period 4: 40; Time Period 5: 30 | 60 | 100 | 80
D | 3 | 2 | 6 | 1 | 35 | 80% | Time Period 3: 20; Time Period 4: 10; Time Period 5: 20 | 28 | 50 | 35
E | 3 | 6 | 9 | 0 | 120
F | 2 | 9 | 11 | 0 | 30
Total PV by time period | [6 empty] | 10 | 20 | 60 | 60 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 200 | 150 | -77 | -27
Cumulative PV by time period | [6 empty] | 10 | 30 | 90 | 150 | 200 | 200 | 200 | 200 | 200 | 200 | 200

## Sheet3
| End of TP5 |  | Remainder of the contract
PV=200 | 0.67 |  | 500
AC=300 |  |  | 746.2687
TCPI
Budget (BAC) | 1000
EV | 500 | 500
AC | 600 | 400
TCPI | 1.25